## Taste Testing Checklist
Project Planner - Main Page
Name of Project | NSLW - Taste Testing Event Checklist
Project Lead
TASK | RESPONSIBLE PARTY | SUGGESTED DATE | DUE DATE | ACTUAL DATE COMPLETED | CURRENT STATUS | ADDITIONAL NOTES
BEFORE TASTE TESTING EVENT
Determine nutrition staff, teacher, and administration buy-in about a Taste Testing event |  | September
Create a team to run the event - Additional staff, teachers, parents, student organizations, community volunteers (See Event Team tab for more information) |  | September | 2024-10-02
Choose a location for the event (See Event Set-Up for more information) |  | September | 2024-10-02
Choose the method of Taste Test sample serving - Table with samples vs directly servings students, etc. (See Taste Testing Ideas tab for more information) |  | September | 2024-10-02 |  |  | Check out the Taste Test Guide on the NSLW SquareMeals page for more ideas!
Decide how the sample will be served - Cups, boats, plates, napkins, etc. |  | August- September
Plan food item purchasing of the NSLW 2024 taste test recipe |  | August- September |  |  |  | *Dependent on purchasing deadlines
Plan purchasing for needed platewares |  | August- September |  |  |  | *Dependent on purchasing deadlines
Plan food item preparation schedule and method with your staff - Food Safety, regular food preparation (See Event Team tab for more information) |  | September | 2024-10-02 |  |  | Pick the best time and area to prepare Taste Testing food items to avoid interfering with normal food production schedules and ensure food safety
Plan the best way to complete Taste Testing ballots (See Ballot tab for more information) |  | September | 2024-10-02 |  |  | Check out the Taste Test Guide on the NSLW SquareMeals page for more ideas!
Print and prepare Taste Testing event materials (See TDA NSLW Materials tab for more information) |  | September | 2024-10-02
Research and provide 1-2 nutrition benefits and/or fun facts about the item you're taste testing |  | September | 2024-10-02
Verify food inventory for Taste Testing event |  | 2024-10-02
Confirm the date and time with the Taste Testing event team |  | 2024-10-02
Determine need of additional materials - pencils, pens, markers, etc. |  | 2024-10-02
Promote the Taste Testing event (See Promotion tab for more information) |  | When NSLW promotion begins | TT Event Date
DAY OF TASTE TESTING EVENT
Announce Taste Testing event during morning announcements |  |  | Morning of TT event
Check-in with Taste Testing event team - Review food safety and other responsibilities |  | 2 hours before the event
Set-up table location with Taste Testing event materials (See Event Set-up tab for more information) |  | 2 hours before the event
Serve Taste Testing event samples |  | During event |  |  |  | Try to avoid food waste!
Take photos and notes of event |  | During event
Handout Taste Testing ballots to students (See Ballot tab for more information) |  | During/after event
AFTER TASTE TESTING EVENT
Collect all ballots and tally the results (See Ballot tab for more information) |  | After event/following week
Share pictures and stories with the TDA at nutrition@texasagriculture.gov |  | After event/following week
Share pictures, stories, and ballot results with your location, students, parents, and community (See Ballot tab for more information) |  | After event/following week |  |  |  | Make sure to use #NSLWBiteSeenAroundTX in your posts!

## Taste Testing Ideas
Project Planner
Name of Project | NSLW - Taste Testing Checklist - TDA Taste Testing Ideas
Project Lead
TASK | EXPLANATION | CONSIDERATIONS
TASTE TESTING EVENT IDEAS
Taste Testing Table | Set up a table with the food samples for students to visit during or after they finish their lunch. You can have students try the food at the table and fill out a ballot at the same time OR allow students to take a sample and ballot back to their seat and turn-in ballots as they leave the lunchroom. | Number of volunteers needed to run the table, Writing utensils needed
Incorporate Into Service Line | At the beginning of the lunch line, have a set up with the taste testing item in its raw form for students to view. Serve the taste testing item in the service line. You can give each student that recieves the sample item a ballot while in line to turn in to a designated location OR have students approach a table to fill out the ballot after they have tried it. | Writing utensils needed
Deliver Taste Testing Samples | Have an event team member walk around the lunchroom to hand out samples and ballots from a cart. Other event team members can assist students with the ballots, discuss the food item, and collect completed ballots and writing utensils. | Number of volunteers needed, Refilling the cart, Writing utensils needed

## TDA NSLW Materials
Project Planner
Name of Project | NSLW - Taste Testing Checklist - TDA NSLW Materials
Project Lead
TASK | RESPONSIBLE PARTY | START DATE | DUE DATE | ACTUAL DATE COMPLETED | CURRENT STATUS | ADDITIONAL NOTES
BEFORE TASTE TESTING EVENT
Visit the NSLW 2024 website page on SquareMeals for Digitial Materials |  | July | October |  |  | www.SquareMeals.org/NSLW
Print any additional materials based on your locations policies, timelines, and/or need for special printing |  | September
Gather and prepare all Taste Testing event materials |  | September | 2024-10-02
Gather any additional materials - ex. pencil/pen/markers for students to fill out ballots |  | September | 2024-10-02

## Event Team
Project Planning Form
Name of Project | NSLW - Taste Testing Checklist - Event Team
Project Lead
TASK | RESPONSIBLE PARTY | START DATE | DUE DATE | CURRENT STATUS | ADDITIONAL NOTES
BEFORE TASTE TESTING EVENT
Determine how many volunteers you will need to run the event based on your location - number of lunch periods, current staff availability, number of students, etc. |  | September |  |  | Consider how you will hand out samples
Contact staff, students, parents, and volunteers willing to prepare and participate in running the Taste Testing event ● When notifying staff, teachers, and admin of the event, ask if anyone would be interested in joining the event team ● Ask student organizations/clubs ● Ask interested parents through the locations website, emails/newsletters, district texts, classroom parent platforms, or flyers sent home with students ● Reach out to local community groups/members that have worked with your location in the past |  | September
Collect contact information for all event team members and create a source of communication ● Email group, google docs, program/software used by location |  | September |  |  | Remember to add memebers as they volunteer!
Provide the event team with all necessary information ● Taste Testing event, time, and location ● Responsibilities of team members ● Food Safety information ● Location policy/instruction to obtain visitors pass and access the event location |  | September | 2024-10-02
Confirm team member availability for the event |  | 2024-10-02 | 2024-10-06
Decide the best schedule for food preparation with your staff |  | September | 2024-10-02 |  | Work with staff to determine the best time and area to prepare Taste Testing food items to avoid interfering with normal food production schedules
DAY OF TASTE TESTING EVENT
Check-in with the event team - review responsibilities, food safety, and answer any questions |  | 2 hours before event
Set-up the Taste Testing event location (See Event Set-Up for more information) |  | 2 hours before event
Prepare Taste Testing food item |  | 2 hours before event |  |  | *Skip this step if your location chooses a different preparation schedule
Plate the Taste Testing food item |  | Shortly before serving |  |  | *Skip this step if your location chooses a different preparation schedule
Serve Taste Testing samples |  | During event
Take pictures and notes |  | Before & during event
Hand out ballots |  | During event |  |  | Based on chosen method
Handout other Taste Testing materials : stickers |  | During event |  |  | If you ordered materials from USDA Team Nutrition
Hand-out any remaining Taste Testing food item samples |  | End of event |  |  | Avoid Food Waste
AFTER THE TASTE TESTING EVENT
Clean up Taste Testing event location and any materials |  | End of event
Collect all completed ballots |  | End of event
Tally results of completed ballots |  | End of event/following week
Thank your Event Team for their time and effort! |  | End of event
Report out the success and learnings from the taste testing event

## Event Set-Up
Project Planner
Name of Project | NSLW - Taste Testing Checklist - Event Set-Up
Project Lead
TASK | RESPONSIBLE PARTY | START DATE | DUE DATE | CURRENT STATUS | ADDITIONAL NOTES
BEFORE THE TASTE TESTING EVENT
Visit the NSLW SquareMeals page for Digital Materials |  | July | October |  | www.SquareMeals.org/NSLW
Choose where you will hold the Taste Testing event - Based on your chosen serving method |  | September | 2024-10-02 |  | Choose a location where students can easily see the event, have enough room to serve samples, handout NSLW materials, and collect ballots
Gather, print, and prepare all NSLW 2024 materials (See TDA NSLW Materials tab for more information) |  | September | 2024-10-02
DAY OF TASTE TESTING EVENT
Set up the Taste Testing event location ●Utilize NSLW 2024 Taste Testing materials ● Make Taste Testing event location look visually appealing to encourage students to participate (See Event Team tab for more information) |  | 2 hours before event
Prepare and set up Taste Testing samples (See Event Team tab for more information) |  | 2 hours before event
Maintain stock of NSLW 2024 materials on table - handouts, stickers, buttons, etc. |  | During event
AFTER THE TASTE TESTING EVENT
Clean up the Taste Testing location and any materials |  | After event

## Promotion
Project Planner
Name of Project | NSLW - Taste Testing Checklist - Promotion
Project Lead
TASK | RESPONSIBLE PARTY | START DATE | DUE DATE | ACTUAL DATE COMPLETED | CURRENT STATUS | ADDITIONAL NOTES
BEFORE THE TASTE TESTING EVENT
Visit the NSLW SquareMeals page for Digital Materials |  | July | October |  |  | www.SquareMeals.org/NSLW
Ensure you have received the Taste Testing event promotion materials you ordered |  | When shipment is received
Research and provide 1-2 nutrition benefits and fun facts about the taste testing food item. Be sure to include them in your announcements and newsletters |  | September - October | 2024-10-02
Inform staff, teachers, admin, students, parents, and community about the Taste Testing event ●Provide admin with information about the event to gain approval or work out any conflicts ● Provide office with announcements to be read in the weeks before NSLW, during NSLW, and on the day of the Taste Testing event ● Provide office with announcements to be read in the weeks before NSLW, during NSLW, and on the day of the Taste Testing event ● Hang-up or display NSLW 2024 and Taste Testing specific promotional materials ● Include information and reminders in the school newsletter and emails ● Ask teachers to make classroom announcement ● Promote on website and social media |  | September - October
DAY OF TASTE TESTING EVENT
Provide office with morning announcement |  |  | Morning of event |  |  | If doing a smaller taste testing event, omit the announcements
Use NSLW 2024 materials to promote Taste Testing location/table |  | Day of event | End of event
Hand out NSLW 2024 materials during each lunch period (See TDA NSLW Materials for more information) |  | Day of event | End of NSLW
Take photos and notes during the event |  | During event | End of event |  |  | Be sure to capture moments throughout the event, inlcuding students taste testing, staff, teachers, admin, event set-up, and event team members!
AFTER THE TASTE TESTING EVENT
Share the Taste Testing event results with the school, parents, and community ● Announcements, webpage, social media, newsletter, classroom pages, district text message, email, flyers, and any local community groups who volunteered |  | After NSLW |  |  |  | Include photos, ballot results, and stories. Make sure to use #NSLWBiteSeenAroundTX in your posts!
Send your photos and stories to nutrition@texasagriculture.gov |  | After NSLW

## Ballot
Project Planner
Name of Project | NSLW - Taste Testing Checklist - Ballot
Project Lead
TASK | RESPONSIBLE PARTY | START DATE | DUE DATE | CURRENT STATUS | ADDITIONAL NOTES
BEFORE THE TASTE TESTING EVENT
Print digital ballots from the NSLW 2024 SquareMeals page |  | September | October |  | www.SquareMeals.org/NSLW
If printing digital ballot - Plan to print your ballots with your other NSLW 2024 materials according to your schools policies, timelines, and/or need for special printing |  | September |  |  | *Make sure you print enough for the number of students you serve
Plan with your event team to determine the best way to handout the ballot based on your chosen serving method |  | September
DAY OF TASTE TESTING EVENT
Handout Taste Testing ballots based on chosen serving method |  | During/After event
Make sure the ballots are being filled out correctly and fully |  | During event
Collect all Taste Testing ballots |  | During/end of event
AFTER TASTE TESTING EVENT
Tally and record the ballot results |  | End of event/following week
Share ballot results with your location, students, parents, and community ● Announcements, webpage, social media, newsletters, classroom pages, district text message, email, flyers, local community groups who volunteered |  | Following week